International School

Capstone Project 2

CMU-SE 451

Project Plan Document

Version 2.0

Date: Feb 17, 2022

Pet Care And Supervision Services

Submitted by

Truong Le Dai

Nguyen Hong Hieu

Tran Thi Chung

Le Quang Van

Approved by

Dr. Nguyen Tan Thuan

.

Proposal Review Panel Representative:

Name					Signature			Date

Capstone Project 2- Mentor: Dr. Nguyen Tan Thuan

Name					Signature			Date

PROJECT INFORMATION

| Project acronym | Pet-Care |  |  |
| --- | --- | --- | --- |
| Project Title | Pet Care And Supervision Services |  |  |
| Start Date | 17 Feb 2022 | End Date | 19 Feb 2022 |
| Lead Institution | International School, Duy Tan University |  |  |
| Project Mentor | Dr. Nguyen Tan Thuan |  |  |
| Scrum master / Project Leader & contact details | Truong Le Dai Email:daicatimmai123v30@gmail.com Tel: 0799400038 |  |  |
| Partner Organization |  |  |  |
| Project Web URL |  |  |  |
| Team members | Name | Email | Tel |
| 24211407122 | Truong Le Dai | daicatimmai123v30@gmail.com | 0799400038 |
| 24211205523 | Nguyen Hong Hieu | nguyenhonghieuit@gmail.com | 0777903474 |
| 24201402277 | Tran Thi Chung | tranchung10a3@gmail.com | 0945228146 |
| 24211401402 | Le Quang Van | vanlequang00@gmail.com | 0898163596 |

Project Plan Document

| Document Title | Project Plan |  |  |  |
| --- | --- | --- | --- | --- |
| Reporting Period |  |  |  |  |
| Author(s) & project | Truong Le Dai, Scrum Master |  |  |  |
| Role | Nguyen Hong Hieu | Member |  |  |
|  | Tran Thi Chung | Member |  |  |
|  | Le Quang Van | Member |  |  |
| Date | 17 Feb 2022 | Filename |  | C2SE.27-Project Plan-PetCare.doc |
| URL |  |  |  |  |
| Access | Project and CMU Program |  |  |  |

# REVISION HISTORY

| Version | Date | Comments | Author | Approval |
| --- | --- | --- | --- | --- |
| 2.0 | 17 Feb 2022 | Draft for comment | C2SE.27 Team | Team |

# DOCUMENT APPROVALS

# The following signatures are required for approval of this document

| Dr. Nguyen Tan Thuan Mentor |  | Date: |
| --- | --- | --- |
| Truong Le Dai Scrum Master |  | Date: |
| Nguyen Hong Hieu Product Owner |  | Date: |
| Tran Thi Chung Member |  | Date: |
| Le Quang Van Member |  | Date: |

# Project Overview

## Project Description

| Project code | C2SE.27 | Contract type | Internal Project |
| --- | --- | --- | --- |
| Customer | DTU University Capstone Committee | /End-User | Pet owners; Veterinary facilities |
| Project Type | Internal | Scrum master | Trương Lê Đại |
| Project Category | Development | Business domain | Veterinary Management |
| Application type | Cross-platform application |  |  |

## Scope and Purpose

    - Purpose

Pet care is an effective support system for those who love to keep pets when providing the best pet care and management services.. We realize the inefficiency in the traditional routines of the vets in Vietnam mainly caused by lack of understanding between related parties, for example: A vet can have many cases in a day which can be new or regular customers and a vet doctor usually has a hard time keeping check of every animal he first takes care of. And on the customer’s side there’s usually the lack of knowledge in animal physiology, which might cause confusion on whether to take their pet to the vet or not, especially in the time of a pandemic like COVID-19.

Pet-care wishes to solve the conflicts and misunderstanding that often occurs between said partners since a regular and easy way to commute has yet to be presented. And as a result the health care process for pets and animals can be as optimal as the state of the art veterinary allows, bringing security of well being for both the pets and their humans.

In addition to pet care services, the system also allows pet owners to monitor their pets through locators, helping to better control pets and reduce negative conditions caused by pets. Not only that, the system also effectively supports pet owners when creating a communication page to help owners find the necessary items as well as liquidate pet products in the best way.

    - Scope

This application consists of a website and a mobile application. Our main goal is to create a vet manager platform that can fit any veterinarian's working style while creating an easy and useful communication channel for the client. customers, and at the same time apply positioning technology to manage hard animals automatically. Create an interactive community to help liquidate pet-related goods for pet owners.

Key functions include basic facilities for uploading, viewing and editing stakeholder profiles; a live chat channel; data visualization; schedule tracking tools; Schedule reminders and notifications and apply pet location technology, manage product liquidations.

## Assumptions and Constraints

| No | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |
| 1 | Customer reviewers will get seven days to approve a milestone document. If no comments are received within this time period, it will be considered as approved. | External Interfaces |
| Constraints |  |  |
| 1 | The project is to be deployed after 10 weeks of development. | Schedule |
| 2 | The budget should be lower than 3000$ | Budget |
| 3 | The user’s information on both ends, the vets and the pet owners are strictly classified and should not be leaked to a third party for malice purposes. | Security |
| 4 | Communication is secured and consistent. | Security |
| 5 | The web application can operate on Google Chrome | Scope |
| 6 | The mobile application can operate on IOS | Scope |

## Project Objectives

    - Standard Objectives

| Metrics | Unit | Committed | Note |
| --- | --- | --- | --- |
| Start Date | dd-mmm-yy | 17 Feb 2022 |  |
| End Date | dd-mmm-yy | 19 Feb 2022 |  |
| Duration | elapsed days | 3 |  |
| Team Size | Person | 4 |  |
| Number of work hours per day for one engineer | Person-hour | 4 |  |

    - Specific Objectives

- Based on the practical need of a communication channel for local veterinary facilities, especially in the time of the pandemic COVID-19, not without considering our resources, we will design and build a management system for pet owners and vets. The main purpose of this application is providing a safe and optimal way to communicate between vets and pet owners, ensuring that the health care process for animals can proceed as smoothly as possible.

- The system will operate with high performance. All data are secured and consistent all the time.

- The application should be easy to use with little to none need of guidance. The UX/UI is designed to adapt to customer satisfaction.

- Taking into consideration the team’s limited resources, the development cost and time lead is to be optimized as much as possible.

- Team members are to have a better understanding of the development processes and technologies after the project.

## Project Risk

| Risk | Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Underestimated time lead | The team wasted quite a lot of time during the initial phase and might not have enough time to finish the complete product. | 4 | 5 | Conduct thorough requirement analysis and prioritize them to create a hierarchy of function points to focus on the most important modules first. |
| People | Team members also have heavy schoolwork and fail to manage time properly. Team members might be occupied for various reasons during the pandemic. | 2 | 3 | All team members are expected to follow predetermined teamwork protocols and treat each other according to the spirit of working in Agile methods that are respect, equality among all, sharing and caring for others. |
| Lack of technical experiences | Team members are lacking in experience in working on an application from start to end. | 3 | 4 | The first month and during the initial phase all team members are to study and research the applied technologies. |
| Difficulty in gathering requirements | The COVID-19 pandemic introduces problems in getting practical requirements from veterinary facilities and people in the pet care industry. | 4 | 5 | Reaching out for members of veterinary facilities and conducting surveys through phone or online. |
| Incorrect Requirements | Lack of practical experience might lead to unrealistic requirement analysis. | 3 | 5 | During the designing and initial phase the team will hold many meetings to brainstorm and analize, prioritize all requirements. |

# Project Development Approach

## Technical Process

    - Reason for selecting

To keep up with today's increasingly changing technology trends, we want a truly flexible and easy project development model to adapt to that change. We use agile methodology in our project, besides using software tools to manage work, assign tasks to team members such as Trello, drive and source code management tools like git. And for project requirements, we use React Native, Spring Boot (android platform) for mobile app development, and React Js, Spring Boot for web development with Mongo, SQL Server database.

    - Agile Methodology

About Agile

The Agile Methodology is a project management method ideal for those that require speed and flexibility to meet client needs and is always focused on improving performance. Applying Agile principles to an enterprise’s internal business processes is much more straightforward than it appears; the methodology’s founders laid it all out in the Agile Manifesto they created in Snowbird.

You don’t plan or design an iteration of a product in advance in the Agile Methodology. Instead, the process evolves in iterative, self-nurturing cycles. You work in short periods called sprints that generally last between two and three weeks, and every team member has to complete a set of tasks assigned to them. At the end of every sprint, you submit the corresponding deliverables. That represents the progress your team has made, and you start the process all over again and work to improve your future everything in the next round of deliverables. Project management practices that incorporate these values allow the client to gradually receive updates and signal priorities or introduce changes when necessary.

Agile Lifecycle

1. Ideation: The very first stage of the Agile workflow is about defining the business scope for each of the project ideas and determining the time and set of tasks to execute such projects. This judgment helps in identifying financial and resource availability so as to conclude which ideas are worth executing!

2. Creation of Sprint Teams: After identifying the project and discussing it with the stakeholders, the agile team members are identified and resources are allocated so as to execute the project. These team members are assigned work responsibilities and the timeframe to complete the same for each of the sprint teams.

3. Iteration: When sprint teams are identified upon discussion and feedback from the stakeholders, the project work is resumed. The team with the objective of launching a workable product at the end of a sprint, start working on the first iteration. As the product goes through many rounds of improvement or iteration, the first iteration usually includes minimum functions. The team can put up more sprints to develop the entire product.

4. Release: At this stage, the product is ready to pass into the production phase. The quality team tests the product functionality and rectifies defects or errors if any.

5. Production: During the production stage, the team must ensure that the product is being launched successfully and guide the users on its usage. Thus, at this phase, the team offers continual support for the product release.

6. Retirement: This is the last stage of the agile software development life cycle. As the name indicates, the product is removed or replaced with a new release. The new product is introduced when the previous product becomes redundant or does not fit the ongoing business model.

    - Scrum Process

About Scrum

Scrum is an agile method, so it follows the principles of Agile Manifesto. In addition, Scrum operates on three core values, also known as Scrip Scripps, including Scrutiny, Inspection and Adaptation.

Based on the empirical process control theory, Scrum uses iterative and incremental algorithms to optimize efficiency and control risk. Scrum is simple, easy to learn and has wide applicability. To be able to use Scrum, we need to understand and apply the elements that make up Scrum include the core values (also known as the "three legs", or the three pillars of Scrum), roles, Events, and Scrum-specific artifacts.

## Quality Management

    - Estimate of Defects to be detected

| Process | Planned found by review | Actual found by review |
| --- | --- | --- |
| Requirement | 10 | 5 |
| Design | 15 | 10 |
| Coding | 50 | 40 |
| Other | 10 | 10 |
| Total | 85 | 65 |

    - Strategy for Meeting Quality Objectives

| Strategy | Expected Benefits |
| --- | --- |
| Do defect prevention using the standard defect prevention guidelines and process; use standards developed in ABC for coding. | 10–20% reduction in defect injection rate and about 2% improvement in productivity |
| Group review of program specs for first few/logically complex use cases. Group review of design docs/first time-generated code by project leader, developer, and one consultant. | Improvement in quality as overall defect removal efficiency will improve; some benefits in productivity as defects will be detected early |
| Introduction of RUP methodology and implementing the project in iterations. Milestone analysis and defect prevention exercise will be done after each Iteration. | Approximately 5% reduction in defect injection rate and 1% improvement in overall productivity |

    - Quality Control

| Review Item | Type of Review | Reviewer | When |
| --- | --- | --- | --- |
| Project plan Project schedule CM Plan | Group review Group review One-person review | Mentor | End of Initiation stage |
| Product backlog, User Story | Group review | Mentor | End of 90% requirement |
| Design document | Group review | Mentor | End of 90% design |
| Sprint backlog | One-person review | Scrum Master | Beginning of each sprint |
| Test case | Group review | Product owner | End of detailed design |
| Code | Group review | Mentor | After coding for first few programs |

    - Measurements Program

| Data to be collected | Purpose | Responsible | When |
| --- | --- | --- | --- |
| Size: No. of KLOC// FP | Manage size of product | SM | At the end of stages |
| Effort: No, hours/day | Estimation evaluate member’s productivity | Team members | Daily |
| Quality: No. defects detected | Evaluate, improve the quality of the product | Team members | Right after the test |
| Schedule | Control schedule, assign appropriate tasks | SM | Weekly and at the end of stages |

## Unit Testing Strategy

## Integration Testing Strategy

- Bottom up Strategy:

The components below are first written and these are integrated first. The integration happens from bottom to top. If the calling component is yet to be developed, it is replaced by a specially written component called a Drive.

When we finish each product backlog, we test it out before we finish.

- Big bang Strategy:

All components are put together at the same time, there is no order, except all are integrated at the same time.

Towards the end of the project, we started to apply this tactic to test the entire application.

## System Testing Strategy

Participating in test cases of each function created in the test case document assesses whether the functions created by the programmers meet the set criteria or not and checks the integrity of the system

# Estimate

## Size

| Software Scale Drivers |  |
| --- | --- |
| Precedented ness | Nominal |
| Development Flexibility | Nominal |
| Architecture / Risk Resolution | Nominal |
| Team Cohesion | Very High |
| Process Maturity | Nominal |

Software Development (Elaboration and Construction)

| Software Cost Drivers |  |  |  |  |
| --- | --- | --- | --- | --- |
| Product |  |  | Personnel |  |
| Required Software Reliability | Nominal |  | Analyst Capability | High |
| Database Size | Nominal |  | Programmer Capability | High |
| Product Complexity | Nominal |  | Personnel Continuity | Nominal |
| Developed for Reusability | High |  | Application Experience | High |
| Documentation Match to Lifecycle Needs | Nominal |  | Platform Experience | High |
|  |  |  | Language and Toolset Experience | High |
| Project |  |  | Platform |  |
| Use of Software Tools |  | High | Time Constraint | Nominal |
| Development |  | Nominal | Storage Constraint | Nominal |
| Required Development Schedule |  | Nominal | Platform Volatility | Nominal |

Derivations:

Effort = 4 Person/months

Schedule = 3 Months

Cost = $2970

## Effort

| Activity/ Process | Total budgeted Effort Usage (pd) | Total % budgeted Effort Usage (%) | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No. | % | No. | % | No. | % | No. | % | No. | % |
| Requirement | $237.6 | 8% | $47.5 | 1.6% | $47.5 | 1.6% | $47.5 | 1.6% | $47.5 | 1.6% | $47.5 | 1.6% |
| Design | $267.3 | 9% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% |
| Coding | $742.5 | 25% | $148.5 | 5% | $148.5 | 5% | $148.5 | 5% | $148.5 | 5% | $148.5 | 5% |
| Unit Testing | $222.8 | 7.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% |
| Testing | $445.5 | 15% | $89.1 | 3% | $89.1 | 3% | $89.1 | 3% | $89.1 | 3% | $89.1 | 3% |
| Deployment | $267.3 | 9% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% |
| Support for Acceptance Test | $193 | 6.5% | $38.6 | 1.3% | $38.6 | 1.3% | $38.6 | 1.3% | $38.6 | 1.3% | $38.6 | 1.3% |
| Project Planning | $267.3 | 9% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% | $53.4 | 1.8% |
| Project monitoring | $222.8 | 7.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% | $44.5 | 1.5% |
| Quality Assurance | $29.7 | 1% | $5.9 | 0.2% | $5.9 | 0.2% | $5.9 | 0.2% | $5.9 | 0.2% | $5.9 | 0.2% |
| Training | $74.25 | 2.5% | $14.8 | 0.5% | $14.8 | 0.5% | $14.8 | 0.5% | $14.8 | 0.5% | $14.8 | 0.5% |
| Total | $2970 | 100% | $594 | 20% | $594 | 20% | $594 | 20% | $594 | 20% | $594 | 20% |

## Schedule

    - Project Milestone & Deliverables

| No | Milestones | Time | Product |
| --- | --- | --- | --- |
| 1 | Initial | 17/02/2022 | Proposal document Project Plan User Story Product Backlog Architecture Design |
| 2 | Development | 26/02/2022 | Database Design |
| 2.1 | Sprint 1 | 26/02/2022 | Test Plan Test Case Sprint Backlog Source code |
| 2.2 | Sprint 2 | 12/03/2022 |  |
| 2.3 | Sprint 3 | 26/03/2022 |  |
| 2.4 | Sprint 4 | 09/04/2022 |  |
| 2.5 | Sprint 5 | 23/04/2022 |  |
| 3 | Project Meeting | 12/05/2021 | Meeting Document |
| 4 | Final Release | 13/05/2022 | Reflection Document |

    - Work Breakdown Structure

    - Detailed Schedule

| No. | Task Name | Duration (Days) | Start | Finish | Assign to |
| --- | --- | --- | --- | --- | --- |
| 1. | Initial | 12 | 14/02/2022 | 25/02/2021 | Team, Mentor |
| 1.1 | Project’s Kick-off Meeting | 1 | 16/02/2022 | 16/02/2022 | Team, Mentor |
| 1.2 | Create Project Proposal Document | 2 | 15/02/2022 | 16/02/2022 | Team, Mentor |
| 1.3 | Create Project Plan Document | 3 | 17/02/2022 | 19/02/2022 | Team, Mentor |
| 1.4 | Create Product Backlog Document | 1 | 20/02/2022 | 21/02/2022 | Team |
| 1.5 | Create User Story | 1 | 20/02/2022 | 21/02/2022 | Team |
| 1.6 | Create Architecture Document | 3 | 22/02/2022 | 24/02/2022 | Team |
| 1.7 | Review Document | 1 | 25/02/2022 | 25/02/2022 | Team |
| 2 | Development | 70 | 26/02/2022 | 06/05/2022 | Team |
| 2.1 | Sprint 1 | 14 | 26/02/2022 | 11/03/2022 | Team |
| 2.1.1 | Sprint Planning Meeting | 1 | 26/02/2022 | 26/02/2022 | Team |
| 2.1.2 | Create Sprint 1 Backlog Document | 1 | 26/02/2022 | 26/02/2022 | Team |
| 2.1.3 | Create Test Plan Document | 1 | 27/02/2022 | 27/02/2022 | Team |
| 2.1.4 | Create Database Document | 1 | 26/02/2022 | 26/02/2022 | Team |
| 2.1.5 | Design UI |  | 26/02/2022 | 26/02/2022 |  |
| 2.1.5.1 | Design UI register (Web) | 1 | 26/02/2022 | 26/02/2022 | Đại |
|  | Design UI register (App) |  |  |  | Đại |
| 2.1.5.2 | Design UI Login (Web) |  |  |  | Hiếu |
|  | Design UI Login (App) |  |  |  | Hiếu |
| 2.1.5.3 | Design UI Pet Owners profile (Web) |  |  |  | Đại |
|  | Design UI Pet Owners profile (App) |  |  |  | Đại |
| 2.1.5.4 | Design UI List Pet Owners (Web) |  |  |  | Chung |
|  | Design UI List Pet Owners (App) |  |  |  | Chung |
| 2.1.5.5 | Design UI List Doctor (Web) |  |  |  | Đại |
|  | Design UI List Doctor (App) |  |  |  | Đại |
| 2.1.5.6 | Design Chat UI(Web) |  |  |  | Hiếu |
|  | Design Chat UI(App) |  |  |  | Hiếu |
| 2.1.6 | Coding | 14 | 26/02/2022 | 11/03/2022 |  |
| 2.1.6.1 | Register (Web) | 3 | 26/02/2022 | 29/02/2022 | Chung |
|  | Register (App) |  |  |  | Đại |
|  | Register API |  |  |  | Đại |
| 2.1.6.2 | Login (Web) |  |  |  | Hiếu |
|  | Login (App) |  |  |  | Văn |
|  | Login API |  |  |  | Văn |
| 2.1.6.3 | Pet Owners profile (Web) | 2 | 28/02/2022 | 03/03/2022 | Hiếu |
|  | Pet Owners profile (App) |  |  |  | Văn |
|  | Pet Owners profile API) |  |  |  | Văn |
| 2.1.6.4 | List Pet Owners (Web) | 3 | 03/03/2022 | 05/03/2022 | Chung |
|  | List Pet Owners (App) |  |  |  | Đại |
|  | List Pet Owners API |  |  |  | Văn |
| 2.1.6.5 | List Doctor (Web) | 3 | 06/03/2022 | 08/03/2022 | Chung |
|  | List Doctor (App) |  |  |  | Đại |
|  | List Doctor API |  |  |  | Đại |
| 2.1.6.6 | Chat real-time (Web) | 3 | 09/03/2022 | 11/03/2022 | Hiếu |
|  | Chat real-time (App) |  |  |  | Đại |
|  | Chat real-time API |  |  |  | Văn |
| 2.1.7 | Design Test case | 12 | 28/02/2022 | 11/03/2022 | Team |
| 2.1.8 | Testing | 12 | 28/02/2022 | 11/03/2022 | Team |
| 2.1.9 | Fix bugs | 12 | 28/02/2022 | 11/03/2022 | Team |
| 2.1.10 | Re-Testing | 1 | 11/03/2022 | 11/03/2022 | Team |
| 2.1.11 | Sprint Review | 1 | 11/03/2022 | 11/03/2022 | Team |
| 2.1.12 | Release Sprint 1 | 1 | 11/03/2022 | 11/03/2022 | Team |
| 2.2 | Sprint 2 | 14 | 12/03/2022 | 25/03/2022 |  |
| 2.2.1 | Sprint planning meeting | 1 | 12/03/2022 | 12/03/2022 | Team |
| 2.2.2 | Create Sprint 2 Backlog | 1 | 12/03/2022 | 12/03/2022 | Team |
| 2.2.3 | Design UI | 1 | 12/03/2022 | 12/03/2022 |  |
| 2.2.3.1 | Design UI Pet list (Web) | 1 | 12/03/2022 | 12/03/2022 | Chung |
|  | Design UI Pet list (App) |  |  |  | Chung |
| 2.2.3.2 | Design UI Appointments (Web) |  |  |  | Văn |
|  | Design UI Appointments (App) |  |  |  | Văn |
| 2.2.3.3 | Design UI View Schedule (Web) |  |  |  | Chung |
|  | Design UI View Schedule (App) |  |  |  | Chung |
| 2.2.3.4 | Design Pet Locate (GPS) UI - (App) |  |  |  | Đại |
| 2.2.3.5 | Design Add Device UI (App) |  |  |  | Đại |
| 2.2.4 | Coding | 13 | 13/03/2022 | 25/03/2022 |  |
| 2.2.4.1 | Pet list (Web) | 1 | 13/03/2022 | 13/03/2022 | Hiếu |
|  | Pet list (App) |  |  |  | Đại |
|  | Pet List (API) |  |  |  | Đại |
| 2.2.4.2 | Appointment (Web) | 2 | 14/03/2022 | 15/03/2022 | Chung |
|  | Appointment (App) |  |  |  | Đại |
|  | Appointment API |  |  |  | Văn |
| 2.2.4.3 | View Schedule (Web) | 1 | 16/03/2022 | 16/03/2022 | Hiếu |
|  | View Schedule (App) |  |  |  | Đại |
|  | View Schedule API |  |  |  | Văn |
| 2.2.4.4 | Pet Locate (GPS) - (App) | 5 | 17/03/2022 | 21/03/2022 | Đại |
| 2.2.4.5 | Add Device (App) | 4 | 22/03/2022 | 25/03/2022 | Đại |
| 2.2.5 | Design Test case | 13 | 13/03/2022 | 25/03/2022 | Team |
| 2.2.6 | Testing | 13 | 13/03/2022 | 25/03/2022 | Team |
| 2.2.7 | Fix bugs | 13 | 13/03/2022 | 25/03/2022 | Team |
| 2.2.8 | Re-Testing | 1 | 25/03/2022 | 25/03/2022 | Team |
| 2.2.9 | Release sprint 2 | 1 | 25/03/2022 | 25/03/2022 | Team |
| 2.3 | Sprint 3 | 14 | 26/03/2022 | 08/04/2022 |  |
| 2.3.1 | Sprint planning meeting | 1 | 26/03/2022 | 26/03/2022 | Team |
| 2.3.2 | Create Sprint 3 Backlog | 1 | 26/03/2022 | 26/03/2022 | Team |
| 2.3.3 | Design UI | 1 | 26/03/2022 | 26/03/2022 |  |
| 2.3.3.1 | Design Create Product Liquidation Post UI (Web) | 1 | 26/03/2022 | 26/03/2022 | Văn |
|  | Design Create Product Liquidation Post UI (App) |  |  |  | Văn |
| 2.3.3.2 | Design Edit Product Liquidation Post UI (Web) |  |  |  | Đại |
|  | Design Edit Product Liquidation Post UI (App) |  |  |  | Đại |
| 2.3.3.3 | Design Delete Product Liquidation Post UI (Web) |  |  |  | Chung |
|  | Design Delete Product Liquidation Post UI (App) |  |  |  | Chung |
| 2.3.3.4 | Design UI notifications (Web) |  |  |  | Hiếu |
|  | Design UI notifications (App) |  |  |  | Hiếu |
| 2.3.3.5 | Design Personal statistical reports UI (Web) |  |  |  | Văn |
|  | Design Personal statistical reports UI (App) |  |  |  | Văn |
| 2.3.4 | Coding | 13 | 27/03/2022 | 08/04/2022 |  |
| 2.3.4.1 | Create Product Liquidation Post (Web) | 3 | 27/03/2022 | 29/03/2022 | Chung |
|  | Create Product Liquidation Post (App) |  |  |  | Đại |
|  | Create Product Liquidation Post API |  |  |  | Đại |
| 2.3.4.2 | Edit Product Liquidation Post (Web) | 3 | 30/03/2022 | 01/04/2022 | Chung |
|  | Edit Product Liquidation Post (App) |  |  |  | Đại |
|  | Edit Product Liquidation Post API |  |  |  | Văn |
| 2.3.4.3 | Delete Product Liquidation Post (Web) | 2 | 02/04/2022 | 03/04/2022 | Chung |
|  | Delete Product Liquidation Post (App) |  |  |  | Đại |
|  | Delete Product Liquidation Post API |  |  |  | Đại |
| 2.3.4.4 | Notifications (Web) | 2 | 04/04/2022 | 05/04/2022 | Hiếu |
|  | Notifications (App) |  |  |  | Đại |
|  | Notifications API |  |  |  | Văn |
| 2.3.4.5 | Personal statistical reports (Web) | 3 | 06/04/2022 | 08/04/2022 | Chung |
|  | Personal statistical reports (App) |  |  |  | Đại |
|  | Personal statistical reports API |  |  |  | Đại |
| 2.3.5 | Design Test case | 13 | 27/03/2022 | 08/04/2022 | Team |
| 2.3.6 | Testing | 13 | 27/03/2022 | 08/04/2022 | Team |
| 2.3.7 | Fix bugs | 13 | 27/03/2022 | 08/04/2022 | Team |
| 2.3.8 | Re-Testing | 1 | 08/04/2022 | 08/04/2022 | Team |
| 2.3.9 | Release sprint 3 | 1 | 08/04/2022 | 08/04/2022 | Team |
| 2.4 | Sprint 4 | 14 | 09/04/2022 | 22/04/2022 |  |
| 2.4.1 | Sprint planning meeting | 1 | 09/04/2022 | 09/04/2022 | Team |
| 2.4.2 | Create Sprint 4 Backlog | 1 | 09/04/2022 | 09/04/2022 | Team |
| 2.4.3 | Design UI | 1 | 09/04/2022 | 09/04/2022 |  |
| 2.4.3.1 | Design Video Call UI (Web) | 1 | 09/04/2022 | 09/04/2022 | Chung |
|  | Design Video Call UI (App) |  |  |  | Chung |
| 2.4.3.2 | Design vet's catalogs and documents UI (Web) |  |  |  | Hiếu |
|  | Design vet's catalogs and documents UI (App) |  |  |  | Hiếu |
| 2.4.3.3 | Design Pet profiles UI (Web) |  |  |  | Đại |
|  | Design Pet profiles UI (App) |  |  |  | Đại |
| 2.4.3.4 | Design Facility profiles UI (Web) |  |  |  | Văn |
|  | Design Facility profiles UI (App) |  |  |  | Văn |
| 2.4.4 | Coding | 13 | 10/04/2022 | 22/04/2022 |  |
| 2.4.4.1 | Video Call (Web) | 4 | 10/04/2022 | 13/04/2022 | Chung |
|  | Video Call (App) |  |  |  | Đại |
| 2.4.4.2 | Vet's catalogs and documents (Web) | 5 | 14/04/2022 | 18/04/2022 | Chung |
|  | Vet's catalogs and documents (App) |  |  |  | Đại |
|  | Vet's catalogs and documents API |  |  |  | Đại |
| 2.4.4.3 | Pet profiles (Web) | 2 | 19/04/2022 | 20/04/2022 | Hiếu |
|  | Pet profiles (App) |  |  |  | Đại |
|  | Pet profiles API |  |  |  | Văn |
| 2.4.4.4 | Facility profiles (Web) | 2 | 21/04/2022 | 22/04/2022 | Hiếu |
|  | Facility profiles (App) |  |  |  | Đại |
|  | Facility profiles API |  |  |  | Văn |
| 2.4.5 | Design Test case | 13 | 10/04/2022 | 22/04/2022 | Team |
| 2.4.6 | Testing | 13 | 10/04/2022 | 22/04/2022 | Team |
| 2.4.7 | Fix bugs | 13 | 10/04/2022 | 22/04/2022 | Team |
| 2.4.8 | Re-Testing | 1 | 22/04/2022 | 22/04/2022 | Team |
| 2.4.9 | Release sprint 4 | 1 | 22/04/2022 | 22/04/2022 | Team |
| 2.5 | Sprint 5 | 14 | 23/04/2022 | 06/05/2022 |  |
| 2.5.1 | Sprint planning meeting | 1 | 23/04/2022 | 23/04/2022 | Team |
| 2.5.2 | Create Sprint 4 Backlog | 1 | 23/04/2022 | 23/04/2022 | Team |
| 2.5.3 | Design UI | 1 | 23/04/2022 | 23/04/2022 |  |
| 2.5.3.1 | Design doctor profile UI (Web) | 1 | 23/04/2022 | 23/04/2022 | Chung |
|  | Design doctor profile UI (App) |  |  |  | Chung |
| 2.5.3.2 | Design UI manage account (Web) |  |  |  | Đại |
|  | Design UI manage account (App) |  |  |  | Đại |
| 2.5.3.3 | Design Search UI (Web) |  |  |  | Hiếu |
|  | Design Search UI (App) |  |  |  | Hiếu |
| 2.5.3.4 | Design Admin Profile UI (Web) |  |  |  | Văn |
|  | Design Admin Profile UI (App) |  |  |  | Văn |
| 2.5.4 | Coding | 13 | 24/04/2022 | 06/05/2022 |  |
| 2.5.4.1 | Doctor profile (Web) | 3 | 24/04/2022 | 26/04/2022 | Chung |
|  | Doctor profile (App) |  |  |  | Đại |
|  | Doctor profile API |  |  |  | Đại |
| 2.5.4.2 | Manage account (Web) | 3 | 27/04/2022 | 29/04/2022 | Hiếu |
|  | Manage account (App) |  |  |  | Đại |
|  | Manage account API |  |  |  | Văn |
| 2.5.4.3 | Search (Web) | 4 | 30/04/2022 | 03/05/2022 | Chung |
|  | Search (App) |  |  |  | Đại |
|  | Search API |  |  |  | Đại |
| 2.5.4.4 | Admin Profile (Web) | 3 | 04/05/2022 | 06/05/2022 | Hiếu |
|  | Admin Profile (App) |  |  |  | Đại |
|  | Admin Profile API |  |  |  | Văn |
| 2.5.5 | Design Test case | 13 | 24/04/2022 | 06/05/2022 | Team |
| 2.5.6 | Testing | 13 | 24/04/2022 | 06/05/2022 | Team |
| 2.5.7 | Fix bugs | 13 | 24/04/2022 | 06/05/2022 | Team |
| 2.5.8 | Re-Testing | 1 | 06/05/2022 | 06/05/2022 | Team |
| 2.5.9 | Release sprint 5 | 1 | 06/05/2022 | 06/05/2022 | Team |
| 2.6 | Complete Document | 5 | 07/05/2022 | 11/05/2022 | Team |
| 3. | Project’s Retrospective Meeting | 1 | 12/05/2022 | 12/05/2022 | Team |
| 4. | Final Release | 3 | 13/05/2022 | 15/05/2022 | Team |
|  | Duration | 92 | 14/02/202 | 15/05/2022 | Team |

## Resource

Specified as in the section Project Team

## Infrastructure

| Work/Product | Purpose | Expected Availability by | Note |
| --- | --- | --- | --- |
| Development Environment |  |  |  |
| Linux Server, Window | Operating System | Initiation stage |  |
| IOS | Operating System | Initiation stage |  |
| MongoDB | DBMS | Initiation stage |  |
| JavaScript | Development language for Web interface | Initiation stage |  |
| React Js | Framework for Web interface | Initiation stage |  |
| React Native | Framework for application interface | Initiation stage |  |
| Node Js | Framework for back-end |  |  |
| Hardware & Software |  |  |  |
| 10GB space on server |  | Initiation stage |  |
| Rational Rose | Design | Initiation stage |  |
| Other Tools |  |  |  |
| Git | Source version control | Definition stage |  |
| Postman | Test API | Initiation stage |  |
| Katalon Studio | Test Application | Initiation stage |  |
| Trello | Manage team work | Initiation stage |  |
| MongoDB | Manage Database | Initiation stage |  |
| Expo Go | Run on mobile | Initiation stage |  |
| Photoshop | Draw Logo | Initiation stage |  |
| Adobe XD | Draw UI/UX | Initiation stage |  |
| Draw.io | Draw Entity Relationship Database, Table Relationship Database | Initiation stage |  |
| Visual Studio Code | Coding | Initiation stage |  |

## Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Technical |  |  |  |
| JavaScript Language | Nguyễn Hồng Hiếu | 5 days | If already trained |
| Detect harmful contents | All members | 10 hours | If already trained |
| React JS | Nguyễn Hồng Hiếu | 5 days | If already trained |
| Node JS | All members | 7 days | If already trained |
| Business domain |  |  |  |
| Process |  |  |  |
| Quality system | All members | 3 hours | If already trained |
| Configuration management(Git tool) | All members | 2 hours | If already trained for CC. For others, on-the- job training |
| Group review | All members | 4 hours | If already trained |
| Defect prevention | All members | 4.5 hours | Mandatory |
| Agile Scrum | All members | 2 hours | Mandatory |

## Finance

| Item | Total Budget | % Budget | Budget in Period |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | W1 - Sept | W2 - Oct | W1 - Oct | W2 - Oct | W1 - Oct | W2 - Oct | W1 - Nov | W1 - Nov | W1 - May | W1 - May |
| Purchases (COTS) | 463.0 | 15.6 | 0 | 96.2 | 0 | 96.2 | 0 | 96.2 | 0 | 96.2 | 0 | 96.2 |
| Team building | 617.8 | 20.8 | 0 | 123.5 | 0 | 123.5 | 0 | 123.5 | 0 | 123.5 | 0 | 123.5 |
| Tools | 308.9 | 10.4 | 0 | 61.78 | 0 | 61.78 | 0 | 61.78 | 0 | 61.78 | 0 | 61.78 |
| Travel costs | 401.0 | 13.5 | 0 | 80.2 | 0 | 80.2 | 0 | 80.2 | 0 | 80.2 | 0 | 80.2 |
| Training | 246.0 | 8.3 | 0 | 49.2 | 0 | 49.2 | 0 | 49.2 | 0 | 49.2 | 0 | 49.2 |
| Review activities | 772.0 | 26.0 | 0 | 154.4 | 0 | 154.4 | 0 | 154.4 | 0 | 154.4 | 0 | 154.4 |
| Other | 160.3 | 5.4 | 0 | 32.0 | 0 | 32.0 | 0 | 32.0 | 0 | 32.0 | 0 | 32.0 |
| Total | 2970 | 100 | 0 | 594 | 0 | 594 | 0 | 594 | 0 | 594 | 0 | 594 |

# Project Organization

# Organization Structure

| Role | Responsibility | Name |
| --- | --- | --- |
| Scrum Master | - Communicate the value of Scrum - Teach the organization on Scrum to maximize business value - Create Plan for Sprint Plan, Daily Review Board, Sprint Review, and thoughts of the meeting Serve as a coach and mentor to members of the Team - Create the Task Board and Sprint Burndown Chart at the - attend seminars on program scrum - Maintain and discuss the group continuously .help team members solve problems encountered in the process. - Facilitating the daily standup (sometimes called the daily scrum) and helping the team reach consensus on each of the three questions. - Helping the team continuously make progress on the project by making sure each person is working on the right tasks, helping to remove any obstacles to the team members’ progress, and protecting the team from distractions. | Trương Lê Đại |
| Product Owner | - Understand users and their needs. - Connect with developers, manage stakeholders. - Describe product features, collect user reviews about the product. - Details of user stories. - Tracks progress towards the release of a product. | Nguyễn Hồng Hiếu |
| Developer | - Responsible for quality. - Responsible for delivering the potentially shippable product of the Application each sprint. - Report progress based on the remaining time. - Self-organized. - Owns the Sprint backlog. | All members |
| Supervisor | - Record group meeting content and group activities | Trương Đình Huy, |
| Reviewer | - Analyze product functions and product requirements - Investigate and review project related documents | Nguyễn Thị Bảo Trang |
| Team Leader | - Back-end dev: server, Database | Trương Lê Đại |
| Team member | -front end dev: UI/UX Designer, Tester, secretary | All Members |

## Project Team

| - Dr. Nguyễn Tấn Thuận |  |
| --- | --- |
| Role | Mentor |
| Responsibility | Provide resource & funding Approve Project plan Review project status Resolve escalated issues Project financial plan |
| Qualification | Development Communication Commitment |
| Type | Training |
| % Effort | 100% |

| Trương Lê Đại |  |
| --- | --- |
| Role | Team Developer |
| Responsibility | Requirement development Requirement analysis Testing |
| Qualification | CRUD operations, interfacing with different layers of the development framework. Unit testing (tools – NUnit, JUnit ) Code coverage concepts and tools Scrum process |
| Type | Training |
| % Effort | 100% |

| Nguyễn Hồng Hiếu |  |
| --- | --- |
| Role | Product Owner |
| Responsibility | Have overall responsibility of the project Project planning and scheduling Task assignment and tracking Reporting Ensure delivery as per contract Interface with other departments as per need Customer interaction Ensure open issues/customer complaints are closed properly |
| Qualification | Development Organizational skill Scrum process Templates and usage Project Management tools Continuous integration tools Development environment setup |
| Type | Training |
| % Effort | 100% |

| Trần Thị Chung, Lê Quang Văn |  |
| --- | --- |
| Role | Team Developer |
| Responsibility | Requirement development Requirement analysis Testing |
| Qualification | CRUD operations, interfacing with different layers of the development framework. Unit testing (tools – NUnit, JUnit ) Code coverage concepts and tools Scrum process |
| Type | Training |
| % Effort | 100% |

# Communication & Reporting

| Audience / Attendees | Topic / Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Scrum Master, Members | Daily meeting | Daily | Google Meet / Messenger Chat |
| Scrum Master, Members | Sprint Planning Meeting | When starting a sprint | Google Meet |
| Scrum Master, Members, Mentor | Sprint Review Meeting | When finishing a sprint | Google Meet / Messenger Chat |
| Scrum Master, Members | Sprint Retrospective | When the sprint review finish | Google Meet |
| Scrum Master, Members | Individual Meeting | When need | Google Meet / Messenger Chat |
| Scrum Master, Members, Mentor | Working report, review problems | Once a week | Google Meet / Messenger Chat |

# Configuration Management

| No | Tool | Content |
| --- | --- | --- |
| 1 | Google Sheet | Track member activities |
| 2 | Google Drive | Track the changing of documents & manage versions of documents. |
| 3 | GitHub | Repositories for open-source code of a project |
| 4 | Trello | Assign the tasks, and set the start and end dates of the tasks |

# Security Aspects

Use authentication to ensure user data integrity.

Encrypting user data to avoid stolen data, decrypting data is also extremely difficult, takes a lot of computational resources and takes a lot of time.

Research on network attack prevention solutions to ensure data security, avoid being exploited and stolen data by hackers.

Deploy project architecture with a high priority in security. Optimized architectural solutions enable the deployment of data security with 99% reliability.

Do not disclose important documents to the outside.

References

| No | Reference item | Issued Date | Source | Note |
| --- | --- | --- | --- | --- |
| 1 | Agile Scrum | 04-Apr-21 | https://www.atlassian.com/agile |  |
|  |  |  | https://www.cprime.com/resources/what-is-agile-what-is-scrum/ |  |
|  |  |  | https://www.agilealliance.org/agile101/ |  |
|  |  |  | The Scrum Framework by International Scrum Institute |  |
| 2 | COCOMO II | 04-Apr-21 | https://www.rose-hulman.edu/class/csse/csse372/201410/SlidePDFs/session12.pdf |  |
| 3 | Software Standards | 05-Apr-21 | https://www.nws.noaa.gov/oh/hrl/developers_docs/General_So ftware_Standards.pdf |  |
|  |  |  | https://standards.ieee.org/standard/12208-2017.html |  |
|  |  |  | https://sw-eng.larc.nasa.gov/ |  |

Definitions and Acronyms

| Acronym | Definition | Note |
| --- | --- | --- |
| PM | Project Manager |  |
| PTL | Project Technical Leader |  |
| QA | Quality Assurance Officer |  |
| CC | Infrastructure Configuration Controller |  |
| DV | Developer |  |
| URD | User Requirement Document |  |
| SRS | Software Requirement Specification |  |
| ADD | Architecture Design Document |  |
| DDD | Detail Design Document |  |
| TP | Test Plan |  |
| TC | Test Case |  |
| SC | Source Code |  |
| CM | Configuration Management |  |
| CSCI | Computer Software Configuration Items |  |
| CI | Configuration Item |  |
| CCB | Change Control Board |  |